## Production Release Checklist
# | Section | Sub-Section | Checklist Item | Detail / Notes | Preview / Stage Ref | Prod Ref | Owner | Priority | Status | Verified By | Date
SECTION 1 – PRE-RELEASE PREREQUISITES
1 |  | General | Prod access confirmed – Adobe Workfront | Verify login to PROD WF tenant | Stage WF tenant | Prod WF tenant | Adobe Admin | High | To Do
2 |  | General | Prod access confirmed – Workfront Fusion | Verify login to PROD Fusion org | Stage Fusion org | Prod Fusion org | Adobe Admin | High | To Do
3 |  | General | Prod access confirmed – Workfront Planning | Verify PROD Planning workspace accessible | Stage Planning | Prod Planning | Adobe Admin | High | To Do
4 |  | General | Prod access confirmed – Adobe I/O Runtime | Verify PROD namespace reachable | 23294-dxcampaignautomation-stage | 14257-918erinrhinoceros | Adobe Admin | High | To Do
5 |  | General | Prod access confirmed – SnapLogic | Verify PROD SnapLogic API credentials active | Stage SnapLogic | Prod SnapLogic | Adobe Admin | High | To Do
6 |  | General | All PREVIEW/Stage scenarios fully tested and signed off | No open bugs; test sign-off document available | Stage | Prod | Dev Team | High | To Do
7 |  | General | IMS / OAuth tokens and API credentials ready for PROD | Store securely; do not reuse Stage tokens | Stage creds | Prod creds | Adobe Admin | High | To Do
8 |  | General | Rollback plan documented and approved | Define steps to revert to previous state if go-live fails | – | Prod | Dev Team | High | To Do
9 |  | General | Prod deployment window approved and communicated | Agreed downtime window; stakeholders notified | – | Prod | Ops Team | High | To Do
SECTION 2 – WORKFRONT CONFIGURATION
▸ Request Queue & Topics
10 |  | Request Queue | Queue 'EAC Enterprise Marketing & Operations Request Queue - Infosys' exists in PROD | Verify queue is live and accessible by APAC/AMER teams | Stage WF | Prod WF | Adobe Admin | High | To Do
11 |  | Request Queue | Queue Topic 'Enterprise Global Campaign Operations Requests' configured | APAC and AMER topics active under the queue | Stage WF | Prod WF | Adobe Admin | High | To Do
▸ Custom Forms
12 |  | Custom Forms | Form: Enterprise Global Campaign Operations Requests-INF active | Issue form; attached to all Campaign Ops requests (#CO #GMOT #MMO) | Stage Form | Prod Form | Dev Team | High | To Do
13 |  | Custom Forms | Form: Campaign Orchestration – Profile and Targeting Criteria AMER active | Task-level targeting form for AMER projects | Stage Form | Prod Form | Dev Team | High | To Do
14 |  | Custom Forms | Form: Campaign Orchestration – Profile and Targeting Criteria APAC active | Task-level targeting form for APAC projects | Stage Form | Prod Form | Dev Team | High | To Do
15 |  | Custom Forms | Form: EAC Enterprise Global Campaign Operations Requests for Tasks-INF active | Task-level request form for all templates | Stage Form | Prod Form | Dev Team | High | To Do
16 |  | Custom Forms | Form: Campaign Orchestration – MCZ Resources INF active | MCZ pre-build task form | Stage Form | Prod Form | Dev Team | High | To Do
17 |  | Custom Forms | Form: E-Mail Governance Approval DX active | Governance approval task form (Approve / Reject field) | Stage Form | Prod Form | Dev Team | High | To Do
18 |  | Custom Forms | All 250+ custom fields verified active via WF Field List report | Run 'DX CO Custom Fields' report in PROD to confirm all fields | Stage Report | Prod Report | Dev Team | High | To Do
▸ Project Templates (4 Templates)
19 |  | Templates | Template: Campaign Orchestration ¦ Email Blast-AMER-INF cloned to PROD | Verify all tasks, forms, owners and task order | Stage Template ID | Prod Template ID | Dev Team | High | To Do
20 |  | Templates | Template: Campaign Orchestration ¦ Email Blast-APAC-INF cloned to PROD |  | Stage Template ID | Prod Template ID | Dev Team | High | To Do
21 |  | Templates | Template: Campaign Orchestration ¦ Newsletter-AMER-INF cloned to PROD |  | Stage Template ID | Prod Template ID | Dev Team | High | To Do
22 |  | Templates | Template: Campaign Orchestration ¦ Newsletter-APAC-INF cloned to PROD |  | Stage Template ID | Prod Template ID | Dev Team | High | To Do
23 |  | Templates | All Prod Template Task IDs documented and available for Fusion config | Required for all watch event filters; note IDs per template | Stage Task IDs | Prod Task IDs | Dev Team | High | To Do
24 |  | Templates | Monitored task IDs noted: Targeting Criteria, Schedule, Solution & Languages | English, Spanish, Portuguese, Japanese, Chinese Simplified, Traditional, Thai, Korean versions | Stage Task IDs | Prod Task IDs | Dev Team | High | To Do
25 |  | Templates | Monitored task IDs noted: Email Governance Approval, Email Program Summary, MCZ Pre-Build Confirmation | Used by watch event filter in scenarios | Stage Task IDs | Prod Task IDs | Dev Team | High | To Do
26 |  | Templates | Monitored task IDs noted: Profile and Content parent task IDs | Used by auto-update watch event (profile/content completion) | Stage Task IDs | Prod Task IDs | Dev Team | High | To Do
27 |  | Templates | Task ordering and dependencies correct in all 4 PROD templates | Re-verify after cloning; ordering can shift | – | Prod | Dev Team | High | To Do
▸ Teams
28 |  | Teams | APAC Team created in PROD and Team ID noted | Team ID stored for Fusion scenario 01 routing | Stage Team ID | Prod Team ID | Adobe Admin | High | To Do
29 |  | Teams | AMER Team created in PROD and Team ID noted |  | Stage Team ID | Prod Team ID | Adobe Admin | High | To Do
30 |  | Teams | Email Governance Team APAC created and Team ID noted | Used in scenario 06 assignment routing | Stage Team ID | Prod Team ID | Adobe Admin | High | To Do
31 |  | Teams | Email Governance Team AMER created and Team ID noted |  | Stage Team ID | Prod Team ID | Adobe Admin | High | To Do
32 |  | Teams | Ops Team APAC configured in PROD | Used in scenario 07 approval routing | Stage | Prod | Adobe Admin | High | To Do
33 |  | Teams | Ops Team AMER configured in PROD |  | Stage | Prod | Adobe Admin | High | To Do
▸ Dashboards & Other
34 |  | Dashboards | Email Governance Dashboard APAC live in PROD | Governance team can access and action from dashboard | Stage | Prod | Dev Team | Medium | To Do
35 |  | Dashboards | Email Governance Dashboard AMER live in PROD |  | Stage | Prod | Dev Team | Medium | To Do
36 |  | Other | Portfolio ID confirmed and documented for Fusion configuration | Portfolio ID used in scenario 01 Set Variable module | Stage Portfolio ID | Prod Portfolio ID | Adobe Admin | High | To Do
37 |  | Other | Marketer ID (automated user) configured in PROD | Used for future marketer assignments in scenario 01 | Stage | Prod | Adobe Admin | High | To Do
38 |  | Other | Layouts configured for Marketer and Ops team views |  | Stage | Prod | Adobe Admin | Medium | To Do
39 |  | Other | Roles configured for APAC and AMER teams |  | Stage | Prod | Adobe Admin | Medium | To Do
40 |  | Other | Operation Queue project exists in PROD (target for request move on governance approval) | Scenario 07 moves approved request here | Stage Project ID | Prod Project ID | Adobe Admin | High | To Do
SECTION 3 – WORKFRONT FUSION: COMMON SETUP
41 |  | Connections | Workfront PROD connection created in Fusion | Used by ALL 19 scenarios; must use PROD WF URL | Stage Connection | Prod Connection | Dev Team | High | To Do
42 |  | Connections | Workfront Planning PROD connection created in Fusion | Used by scenarios 04, 06, 11, 13, 15 | Stage Connection | Prod Connection | Dev Team | High | To Do
43 |  | Connections | Adobe I/O Runtime PROD connection configured | IMS auth; used by all I/O module calls | Stage Connection | Prod Connection | Dev Team | High | To Do
44 |  | Connections | SnapLogic PROD API credentials stored in Fusion | OAuth token + PROD API URL | Stage Creds | Prod Creds | Dev Team | High | To Do
45 |  | Connections | IMS / OAuth token for Adobe I/O auth available in PROD | Separate from Stage token | Stage Token | Prod Token | Adobe Admin | High | To Do
46 |  | Datastore | Fusion Datastore configured for PROD (document ID tracking) | Used in scenario 13 to prevent duplicate builds | Stage Datastore | Prod Datastore | Dev Team | High | To Do
47 |  | Webhooks | All webhook URLs regenerated in PROD for each webhook scenario | Webhooks generate new URLs in PROD; all callers must be updated | Preview URLs | New Prod URLs | Dev Team | High | To Do
48 |  | General | All scenario names renamed from [PREVIEW] to PROD equivalent | Remove [PREVIEW] prefix to avoid confusion | [PREVIEW] prefix | No prefix | Dev Team | Low | To Do
SECTION 4 – FUSION: WATCH EVENT SCENARIOS (4 Scenarios)
▸ Watch 1: Campaign Orchestration – new Request (APAC,AMER)
49 |  | Watch 1 | Scenario cloned from PREVIEW to PROD |  | Preview Scenario | Prod Scenario | Dev Team | High | To Do
50 |  | Watch 1 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
51 |  | Watch 1 | Queue filter: 'DX - Campaign Operation Requests' queue topic configured | Ensure PROD queue name matches exactly | Preview | Prod | Dev Team | High | To Do
52 |  | Watch 1 | HTTP POST module: webhook URL of scenario 01 updated to PROD URL | Watch event fires → calls scenario 01 webhook | Preview S01 URL | Prod S01 URL | Dev Team | High | To Do
53 |  | Watch 1 | Scenario activated (ON) in PROD |  | – | Prod | Dev Team | High | To Do
54 |  | Watch 1 | Smoke test: Submit test request → scenario fires and calls scenario 01 | Confirm event captured and payload forwarded | – | Prod | Dev Team | High | To Do
▸ Watch 2: Project Tasks Update (APAC, AMER – Single & Multi)
55 |  | Watch 2 | Scenario cloned from PREVIEW to PROD |  | Preview Scenario | Prod Scenario | Dev Team | High | To Do
56 |  | Watch 2 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
57 |  | Watch 2 | All monitored template task IDs updated (Targeting Criteria, Schedule, Solution & Languages, Governance, Email Summary, MCZ Pre-Build, all language version tasks) | 4 templates × all monitored task IDs | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
58 |  | Watch 2 | Scenario activated (ON) in PROD |  | – | Prod | Dev Team | High | To Do
59 |  | Watch 2 | Smoke test: Manually update a monitored task → scenario fires | Confirm scenario detects update across all 4 templates | – | Prod | Dev Team | High | To Do
▸ Watch 3: Project Tasks Update (Profile & Content Auto Update)
60 |  | Watch 3 | Scenario cloned from PREVIEW to PROD |  | Preview Scenario | Prod Scenario | Dev Team | High | To Do
61 |  | Watch 3 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
62 |  | Watch 3 | Profile and Content parent task IDs updated for all 4 PROD templates |  | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
63 |  | Watch 3 | Scenario activated (ON) in PROD |  | – | Prod | Dev Team | High | To Do
64 |  | Watch 3 | Smoke test: Complete all child tasks → parent auto-completes → scenario fires |  | – | Prod | Dev Team | High | To Do
▸ Watch 4: Campaign Orchestration – Watch SnapLogic Doc Update
65 |  | Watch 4 | Scenario cloned from PREVIEW to PROD |  | Preview Scenario | Prod Scenario | Dev Team | High | To Do
66 |  | Watch 4 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
67 |  | Watch 4 | MCZ Pre-Build Confirmation task document section filter configured for PROD | Watches for SnapLogic-created document versions | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
68 |  | Watch 4 | HTTP module: webhook URL of scenario 15 updated to PROD URL |  | Preview S15 URL | Prod S15 URL | Dev Team | High | To Do
69 |  | Watch 4 | Scenario activated (ON) in PROD |  | – | Prod | Dev Team | High | To Do
70 |  | Watch 4 | Smoke test: Document version created on MCZ Pre-Build task → scenario fires |  | – | Prod | Dev Team | High | To Do
SECTION 5 – FUSION: WEBHOOK SCENARIOS (15 Scenarios)
▸ Scenario 00 – External Lookup Language Selection
71 |  | Scen 00 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
72 |  | Scen 00 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
73 |  | Scen 00 | Template task IDs updated for APAC and AMER Single CTA templates (language extraction) | Used to build language dropdown values | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
74 |  | Scen 00 | Webhook URL updated in Request Form External Lookup configuration | External lookup on request form must point to PROD webhook | Preview Webhook | Prod Webhook | Dev Team | High | To Do
75 |  | Scen 00 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
76 |  | Scen 00 | Smoke test: Open request form → Language dropdown populates correctly for APAC and AMER |  | – | Prod | Dev Team | High | To Do
▸ Scenario 01 – New Request to Marketer & Operations Project
77 |  | Scen 01 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
78 |  | Scen 01 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
79 |  | Scen 01 | APAC and AMER Team IDs updated in Set Variable module |  | Preview Team IDs | Prod Team IDs | Dev Team | High | To Do
80 |  | Scen 01 | Portfolio ID updated in Set Variable module |  | Preview Portfolio ID | Prod Portfolio ID | Dev Team | High | To Do
81 |  | Scen 01 | All 4 project template IDs updated in Set Variable module |  | Preview Template IDs | Prod Template IDs | Dev Team | High | To Do
82 |  | Scen 01 | Base URL updated to PROD Workfront URL (for navigation links in update messages) |  | Preview Base URL | Prod Base URL | Dev Team | High | To Do
83 |  | Scen 01 | Marketer ID updated |  | Preview | Prod | Dev Team | High | To Do
84 |  | Scen 01 | APAC and AMER team owner routing updated with PROD team owner data |  | Preview | Prod | Dev Team | High | To Do
85 |  | Scen 01 | HTTP module: webhook URL of scenario 02 updated to PROD URL |  | Preview S02 URL | Prod S02 URL | Dev Team | High | To Do
86 |  | Scen 01 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
87 |  | Scen 01 | Smoke test: Request submitted → PROD project created, correct template and owner assigned |  | – | Prod | Dev Team | High | To Do
▸ Scenario 02 – Request Content Mapping to Task
88 |  | Scen 02 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
89 |  | Scen 02 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
90 |  | Scen 02 | APAC-specific targeting field mappings verified (verticals, personas, roles, GTM segment, POI, etc.) | All fields in APAC update module mapped to correct PROD task form fields | Preview | Prod | Dev Team | High | To Do
91 |  | Scen 02 | AMER-specific targeting field mappings verified (NOAM/LATAM segments, Product Buying Group, industry, suppressions, etc.) | All fields in AMER update module mapped correctly | Preview | Prod | Dev Team | High | To Do
92 |  | Scen 02 | HTTP module: webhook URL of scenario 04 (Planning update) updated to PROD URL |  | Preview S04 URL | Prod S04 URL | Dev Team | High | To Do
93 |  | Scen 02 | Language task cancellation logic verified – unused language tasks set to Cancelled | All language tasks EXCEPT selected language marked Cancelled at 100% | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
94 |  | Scen 02 | Draft.js HTML conversion module functional in PROD |  | Preview | Prod | Dev Team | High | To Do
95 |  | Scen 02 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
96 |  | Scen 02 | Smoke test: Request converted → language task updated, unused tasks cancelled |  | – | Prod | Dev Team | High | To Do
▸ Scenario 03 – New Request Overview
97 |  | Scen 03 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
98 |  | Scen 03 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
99 |  | Scen 03 | Adobe I/O overviewSummary endpoint updated to PROD URL | Preview: /23294-dxcampaignautomation-stage/v1/overviewsummary | Stage: .../overviewsummary | Prod: /14257-918erinrhinoceros/v1/overviewSummary | Dev Team | High | To Do
100 |  | Scen 03 | HTTP module: webhook URL calling scenario 05 (validation) updated to PROD URL |  | Preview S05 URL | Prod S05 URL | Dev Team | High | To Do
101 |  | Scen 03 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
102 |  | Scen 03 | Smoke test: Overview generated and posted on Issue, Project, and Language task |  | – | Prod | Dev Team | High | To Do
▸ Scenario 04 – Watch Updates on Projects & Tasks (Marketers & Ops)
103 |  | Scen 04 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
104 |  | Scen 04 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
105 |  | Scen 04 | Workfront Planning connection updated to PROD |  | Preview Planning Conn | Prod Planning Conn | Dev Team | High | To Do
106 |  | Scen 04 | Requests Planning table ID updated in all modules |  | Preview Table ID | Prod Table ID | Dev Team | High | To Do
107 |  | Scen 04 | Campaign Request Data Planning table ID updated in all modules |  | Preview Table ID | Prod Table ID | Dev Team | High | To Do
108 |  | Scen 04 | Draft.js HTML conversion for email body functional |  | Preview | Prod | Dev Team | High | To Do
109 |  | Scen 04 | All router filters and template task IDs updated |  | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
110 |  | Scen 04 | HTTP module: webhook URL calling scenario 05 updated to PROD URL |  | Preview S05 URL | Prod S05 URL | Dev Team | High | To Do
111 |  | Scen 04 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
112 |  | Scen 04 | Smoke test: Planning records created and updated on request conversion |  | – | Prod | Dev Team | High | To Do
▸ Scenario 05 – Marketer Project Tasks Validation
113 |  | Scen 05 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
114 |  | Scen 05 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
115 |  | Scen 05 | Workfront Planning connection updated (Field List table) |  | Preview Planning Conn | Prod Planning Conn | Dev Team | High | To Do
116 |  | Scen 05 | All template task IDs updated in router filters (Targeting, Content, Language, Profile, Governance IDs across all 4 templates) | 4 templates × all task types | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
117 |  | Scen 05 | Webhook URL of scenario 05.1 updated to PROD URL in HTTP module |  | Preview S05.1 URL | Prod S05.1 URL | Dev Team | High | To Do
118 |  | Scen 05 | Webhook URL of scenario 06 updated to PROD URL in HTTP module |  | Preview S06 URL | Prod S06 URL | Dev Team | High | To Do
119 |  | Scen 05 | APJ SFDC task template IDs updated in APAC sub-route | Used for APAC Salesforce campaign ID generation = Yes flow | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
120 |  | Scen 05 | Email Governance template task IDs updated |  | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
121 |  | Scen 05 | Profile and Content task IDs updated for completion aggregation check | Must equal 2 completed tasks before governance trigger fires | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
122 |  | Scen 05 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
123 |  | Scen 05 | Smoke test: Task update → change tracked, validation triggered, correct route selected |  | – | Prod | Dev Team | High | To Do
▸ Scenario 05.1 – Validation Summary
124 |  | Scen 05.1 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
125 |  | Scen 05.1 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
126 |  | Scen 05.1 | Workfront Planning connections updated (Validation_rules table + Field List table) |  | Preview Table IDs | Prod Table IDs | Dev Team | High | To Do
127 |  | Scen 05.1 | Adobe I/O validationSummary endpoint updated to PROD URL | Preview: /23294-.../v1/validationsummary | Stage: .../validationsummary | Prod: /14257-918erinrhinoceros/v1/validationSummary | Dev Team | High | To Do
128 |  | Scen 05.1 | Template task IDs updated (Target Criteria, Language Content, Email Governance for all 4 templates) | Determines route taken (targeting vs content vs governance) | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
129 |  | Scen 05.1 | Sleep guards (3-second) retained before Planning table reads | Required to avoid race conditions on Planning record retrieval | Preview | Prod | Dev Team | Medium | To Do
130 |  | Scen 05.1 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
131 |  | Scen 05.1 | Smoke test: Validation runs → Critical issue blocks task at 50%; Non-critical posts advisory note |  | – | Prod | Dev Team | High | To Do
▸ Scenario 06 – Overall Summary & Email Governance Assignment
132 |  | Scen 06 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
133 |  | Scen 06 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
134 |  | Scen 06 | Workfront Planning connection updated (Field List table) |  | Preview Planning Conn | Prod Planning Conn | Dev Team | High | To Do
135 |  | Scen 06 | Email Governance Team APAC ID updated |  | Preview Team ID | Prod Team ID | Dev Team | High | To Do
136 |  | Scen 06 | Email Governance Team AMER ID updated |  | Preview Team ID | Prod Team ID | Dev Team | High | To Do
137 |  | Scen 06 | Email Governance template task IDs updated for all 4 templates |  | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
138 |  | Scen 06 | Adobe I/O overAllSummary endpoint updated to PROD URL |  | Stage: Stage endpoint | Prod: /14257-918erinrhinoceros/v1/overAllSummary | Dev Team | High | To Do
139 |  | Scen 06 | Email Governance assignee notification HTML message reviewed for PROD | Verify links and team names are correct for PROD | Preview | Prod | Dev Team | Medium | To Do
140 |  | Scen 06 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
141 |  | Scen 06 | Smoke test: All tasks complete → summary posted, governance team assigned and notified by region |  | – | Prod | Dev Team | High | To Do
▸ Scenario 07 – Email Governance Approval
142 |  | Scen 07 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
143 |  | Scen 07 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
144 |  | Scen 07 | APAC and AMER Ops team IDs updated |  | Preview Team IDs | Prod Team IDs | Dev Team | High | To Do
145 |  | Scen 07 | Pre-check, Email Summary, Build SFDC template task IDs updated for all 4 templates | Sub-routes A, B, C require PROD task IDs | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
146 |  | Scen 07 | Language content task IDs and APJ SFDC build task IDs updated | Used for APAC campaign with SF ID generation = Yes | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
147 |  | Scen 07 | Operation Queue project ID updated (target for approved request move) |  | Preview Project ID | Prod Project ID | Dev Team | High | To Do
148 |  | Scen 07 | Email Governance Approval template task IDs updated |  | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
149 |  | Scen 07 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
150 |  | Scen 07 | Smoke test (Approval): Governance approves → project moved to Ops Queue, marketer notified |  | – | Prod | Dev Team | High | To Do
151 |  | Scen 07 | Smoke test (Rejection): Governance rejects → project status = Cancelled, marketer notified |  | – | Prod | Dev Team | High | To Do
152 |  | Scen 07 | Corner case: Governance marks task complete without approval value → task reset to New | Filter: status = CPL but Approval field empty → revert to New | Preview | Prod | Dev Team | High | To Do
▸ Scenario 08 – Marketer Access Revoke after Email Governance Approval
153 |  | Scen 08 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
154 |  | Scen 08 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
155 |  | Scen 08 | Targeting and Content task IDs updated for access revocation scope | Only completed Targeting + Content tasks affected; not governance/build tasks | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
156 |  | Scen 08 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
157 |  | Scen 08 | Smoke test: Post-approval → marketer access set to VIEW on completed content/targeting tasks |  | – | Prod | Dev Team | High | To Do
▸ Scenario 11 – Email Program Summary Changes
158 |  | Scen 11 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
159 |  | Scen 11 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
160 |  | Scen 11 | Workfront Planning connection updated |  | Preview Planning Conn | Prod Planning Conn | Dev Team | High | To Do
161 |  | Scen 11 | Email Program Summary template task IDs updated for all 4 templates | Webhook filter on this task ID | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
162 |  | Scen 11 | Email Governance task ID filter updated | Route 1 checks if Email Gov is Complete before proceeding | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
163 |  | Scen 11 | Program Shell Planning table connected to PROD (region, CTA type, gated/ungated, sub-region mapping) | Japan sub-region handled separately | Preview Table ID | Prod Table ID | Dev Team | High | To Do
164 |  | Scen 11 | MCZ Program Name and Folder name build logic verified in Fusion (built from Requests Planning table) | Regex and string construction rules match PROD naming conventions | Preview | Prod | Dev Team | High | To Do
165 |  | Scen 11 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
166 |  | Scen 11 | Smoke test: Email Program Summary task completes → MCZ pre-build fields (Shell, Name, Folder) populated in task form |  | – | Prod | Dev Team | High | To Do
▸ Scenario 12 – MCZ Pre-Build Changes
167 |  | Scen 12 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
168 |  | Scen 12 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
169 |  | Scen 12 | MCZ Pre-Build Confirmation task IDs updated for all 4 templates | Webhook filter on MCZ Program Shell, Program Name, Program Folder field changes | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
170 |  | Scen 12 | Sync to Issue and Task custom form verified for PROD field names | Route 1: template changes; Route 2: field changes (Shell, Name, Folder) | Preview | Prod | Dev Team | High | To Do
171 |  | Scen 12 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
172 |  | Scen 12 | Smoke test: Update MCZ fields in task → synced to Issue record and task comments |  | – | Prod | Dev Team | High | To Do
▸ Scenario 13 – MCZ Build JSON
173 |  | Scen 13 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
174 |  | Scen 13 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
175 |  | Scen 13 | Workfront Planning connections updated (Requests, Campaign Request Data, Tokens, MCZ Sync Constants tables) | 4 separate Planning connections required | Preview Table IDs | Prod Table IDs | Dev Team | High | To Do
176 |  | Scen 13 | MCZ Build template task IDs updated for all 4 templates | Main filter: newState.status = CPL AND templateTask matches one of 4 IDs | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
177 |  | Scen 13 | Adobe I/O mczSyncObject endpoint updated to PROD URL |  | Stage: .../mczSyncObject | Prod: /14257-918erinrhinoceros/v1/mczSyncObject | Dev Team | High | To Do
178 |  | Scen 13 | Fusion Datastore updated to PROD datastore for document ID dedup tracking | overwrite: false prevents duplicate builds | Preview Datastore | Prod Datastore | Dev Team | High | To Do
179 |  | Scen 13 | Document upload to MCZ Pre-Build Confirmation task section verified | Document created in PROD WF task document section | Preview | Prod | Dev Team | High | To Do
180 |  | Scen 13 | HTTP module: webhook URL of scenario 14 updated to PROD URL |  | Preview S14 URL | Prod S14 URL | Dev Team | High | To Do
181 |  | Scen 13 | Prerequisite guard (Sub-Route B) task IDs updated | Guards against out-of-sequence build task completion | Preview Task IDs | Prod Task IDs | Dev Team | High | To Do
182 |  | Scen 13 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
183 |  | Scen 13 | Smoke test: MCZ Build task marked complete → JSON assembled, uploaded as doc, notification posted on task |  | – | Prod | Dev Team | High | To Do
▸ Scenario 14 – SnapLogic API Call
184 |  | Scen 14 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
185 |  | Scen 14 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
186 |  | Scen 14 | SnapLogic PROD API URL configured in HTTP Module 2 | Verify with SnapLogic team | Preview API URL | Prod API URL | Dev Team | High | To Do
187 |  | Scen 14 | IMS/OAuth PROD credentials configured in HTTP Module 1 (authentication) |  | Preview Creds | Prod Creds | Dev Team | High | To Do
188 |  | Scen 14 | Document download module connected to PROD Workfront | Binary → string conversion functional | Preview | Prod | Dev Team | High | To Do
189 |  | Scen 14 | syncLevel filter verified (only payloads with syncLevel attribute proceed) |  | Preview | Prod | Dev Team | High | To Do
190 |  | Scen 14 | Error handler for invalid JSON document format active |  | Preview | Prod | Dev Team | Medium | To Do
191 |  | Scen 14 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
192 |  | Scen 14 | Smoke test: Document ID received → document fetched, parsed, SnapLogic PROD API called |  | – | Prod | Dev Team | High | To Do
▸ Scenario 15 – SnapLogic / Marketo References
193 |  | Scen 15 | Scenario cloned to PROD |  | Preview | Prod | Dev Team | High | To Do
194 |  | Scen 15 | Workfront connection updated to PROD |  | Preview WF Conn | Prod WF Conn | Dev Team | High | To Do
195 |  | Scen 15 | Workfront Planning connection updated (Requests table – Sync Status field) |  | Preview Table ID | Prod Table ID | Dev Team | High | To Do
196 |  | Scen 15 | Adobe I/O processResponse endpoint updated to PROD URL |  | Stage: Stage endpoint | Prod: /14257-918erinrhinoceros/v1/processResponse | Dev Team | High | To Do
197 |  | Scen 15 | Success route: Marketo Program URL and Folder URL extraction verified | Links must navigate to PROD Marketo | Preview | Prod | Dev Team | High | To Do
198 |  | Scen 15 | Error routes: All 5 types handled (parent folder not found, already exists, search key failure, cache, missing folder/program name) | Each error type has dedicated logic path | Preview | Prod | Dev Team | High | To Do
199 |  | Scen 15 | On error: Task status reset to In Progress in Requests table for retry |  | Preview | Prod | Dev Team | High | To Do
200 |  | Scen 15 | Scenario activated (ON) |  | – | Prod | Dev Team | High | To Do
201 |  | Scen 15 | Smoke test (Success): SnapLogic response received → Marketo links posted on project, Planning Sync Status updated |  | – | Prod | Dev Team | High | To Do
202 |  | Scen 15 | Smoke test (Error): Error response → error details posted, task reset to In Progress |  | – | Prod | Dev Team | High | To Do
SECTION 6 – ADOBE I/O RUNTIME ACTIONS (5 Actions)
203 |  | General | All 5 actions deployed under package 'fusion-dev' in PROD Adobe I/O namespace | Package name must be fusion-dev | Namespace: 23294-dxcampaignautomation-stage | Namespace: 14257-918erinrhinoceros | Adobe Admin | High | To Do
204 |  | General | require-adobe-auth: true confirmed on all 5 actions in PROD | Security requirement; do not deploy without auth | Stage config | Prod config | Adobe Admin | High | To Do
▸ Action 1 – validationSummary
205 |  | validationSummary | Action deployed and PROD endpoint active |  | Stage: /23294-.../v1/validationsummary | Prod: /14257-918erinrhinoceros/v1/validationSummary | Dev Team | High | To Do
206 |  | validationSummary | Test with APAC payload: Subject (≤90 chars), Preview Text (40–130), SFDC ID (^701[A-Za-z0-9]{15}$), CTA URL (HTTPS), Banner Image, Launch Date (business days) | All 6 validation types must return correct results | Stage | Prod | Dev Team | High | To Do
207 |  | validationSummary | Test with AMER payload: SFDC Internal Campaign ID, Marketing Hub URL, NOAM/LATAM targeting fields |  | Stage | Prod | Dev Team | High | To Do
208 |  | validationSummary | CTA URL parameter check: s_iid and s_rtid mandatory; trackingid, mv, click advisory; differs by region | Verify APAC vs AMERICAS logic correctly applied | Stage | Prod | Dev Team | High | To Do
209 |  | validationSummary | Multi-CTA validation: all required fields checked for each CTA section (1–5) based on numberOfCTAs value | Empty field check across all sections | Stage | Prod | Dev Team | High | To Do
210 |  | validationSummary | Response: Critical Issues vs Recommendations split correctly; HTML summary returned |  | Stage | Prod | Dev Team | High | To Do
▸ Action 2 – overAllSummary
211 |  | overAllSummary | Action deployed and PROD endpoint active |  | Stage: Stage endpoint | Prod: /14257-918erinrhinoceros/v1/overAllSummary | Dev Team | High | To Do
212 |  | overAllSummary | Test with full campaign field payload → formatted HTML summary output verified | Summary posted as Workfront project update | Stage | Prod | Dev Team | High | To Do
▸ Action 3 – overviewSummary
213 |  | overviewSummary | Action deployed and PROD endpoint active |  | Stage: /23294-.../v1/overviewsummary | Prod: /14257-918erinrhinoceros/v1/overviewSummary | Dev Team | High | To Do
214 |  | overviewSummary | Test with Issue + Project + Language content data → overview generated and returned | Overview posted on Issue, Project and Language task | Stage | Prod | Dev Team | High | To Do
▸ Action 4 – mczSyncObject
215 |  | mczSyncObject | Action deployed and PROD endpoint active |  | Stage: /23294-.../v1/mczSyncObject | Prod: /14257-918erinrhinoceros/v1/mczSyncObject | Dev Team | High | To Do
216 |  | mczSyncObject | Test with full payload (request data + campaign data + program shell + tokens + sync constants) → transferSet JSON returned |  | Stage | Prod | Dev Team | High | To Do
217 |  | mczSyncObject | Token matching: request fields matched to token definitions, then campaign data fields matched; merged into token array | Sub-routes 1, 2, 4 logic verified | Stage | Prod | Dev Team | High | To Do
218 |  | mczSyncObject | APAC tokens verified: 77 tokens across CTA sections 1–5 generated correctly | Tokens S.No 1–77 from documentation | Stage | Prod | Dev Team | High | To Do
219 |  | mczSyncObject | AMER tokens verified: same 77 tokens with AMER-specific values |  | Stage | Prod | Dev Team | High | To Do
▸ Action 5 – processResponse
220 |  | processResponse | Action deployed and PROD endpoint active |  | Stage: Stage endpoint | Prod: /14257-918erinrhinoceros/v1/processResponse | Dev Team | High | To Do
221 |  | processResponse | Success response: Marketo Program URL and Folder URL extracted and returned correctly | Links to PROD Marketo program and folder | Stage | Prod | Dev Team | High | To Do
222 |  | processResponse | Error response: all 5 error types handled with descriptive output and next steps | Parent folder not found, already exists, search key failure, cache, missing name | Stage | Prod | Dev Team | High | To Do
SECTION 7 – WORKFRONT PLANNING TABLES
▸ Core Tables
223 |  | Core | Requests Table exists in PROD Planning workspace | Primary campaign record; central data source for Fusion scenarios | Stage | Prod | Dev Team | High | To Do
224 |  | Core | Requests Table: all key fields present (Request ID, WF issue ID, project ID, campaign launch date, targeting criteria, POI details, fiscal details, Campaign Request Data record reference) |  | Stage | Prod | Dev Team | High | To Do
225 |  | Core | Campaign Request Data Table exists in PROD | One record per request × language combination | Stage | Prod | Dev Team | High | To Do
226 |  | Core | Campaign Request Data Table: all CTA content fields present for CTA sections 1–5 (email subject, headline, body, CTA text, CTA URL, image, SFDC fields) |  | Stage | Prod | Dev Team | High | To Do
227 |  | Core | Field List Table exists and populated in PROD | Field Name, Label, Type, Region, Description, Tokens, Planning Table references; used by scenarios 05, 05.1, 06 | Stage | Prod | Dev Team | High | To Do
228 |  | Core | Tokens Table populated in PROD – all 77 tokens present | Token names, types, planning field mappings, ref/ver metadata | Stage | Prod | Dev Team | High | To Do
229 |  | Core | Program Shell Table populated in PROD with correct shell mapping matrix | Region (APAC/AMER), CTA type (single/multi), gated/ungated, sub-region (Japan) combinations covered | Stage | Prod | Dev Team | High | To Do
230 |  | Core | Program Shell mapping verified for APAC: all sub-region and gating type combinations |  | Stage | Prod | Ops Team | High | To Do
231 |  | Core | Program Shell mapping verified for AMER: all combinations |  | Stage | Prod | Ops Team | High | To Do
232 |  | Core | MCZ Sync Constants Table populated with correct feature toggle values | Program name replacement, folder name replacement flags configured correctly | Stage | Prod | Dev Team | High | To Do
233 |  | Core | POI List Table populated (all Adobe products, DB values, token attributes) | Used for POI mapping and token generation | Stage | Prod | Dev Team | High | To Do
234 |  | Core | Fiscal Table populated with Adobe fiscal calendar data (FY, fiscal quarter, fiscal month) | Based on campaign launch date → fiscal values derived and passed to MCZ as tokens | Stage | Prod | Dev Team | High | To Do
235 |  | Core | Marketo Fields Table populated (internal Fusion logic reference) |  | Stage | Prod | Dev Team | Medium | To Do
236 |  | Core | Marketo Field References Table populated (product labels, DB values, Marketo mappings, industry classifications) |  | Stage | Prod | Dev Team | High | To Do
▸ Lookup Tables (11 Tables)
237 |  | Lookup | Lookup: Solutions – all solution abbreviations and attributes populated | Solution abbreviations used in token generation and naming | Stage | Prod | Dev Team | High | To Do
238 |  | Lookup | Lookup: Target Contact Regions – all region codes present |  | Stage | Prod | Dev Team | High | To Do
239 |  | Lookup | Lookup: Target Contact Country – all country codes and abbreviations present | Country mapped to country code for token generation | Stage | Prod | Dev Team | High | To Do
240 |  | Lookup | Lookup: Target Contact Language – all APAC and AMER languages present | Language codes used for task creation and token values | Stage | Prod | Dev Team | High | To Do
241 |  | Lookup | Lookup: Target Contact MarketArea – populated |  | Stage | Prod | Dev Team | Medium | To Do
242 |  | Lookup | Lookup: Target Company Industry – all industry verticals present | Used in targeting criteria and token generation | Stage | Prod | Dev Team | High | To Do
243 |  | Lookup | Lookup: Target Contact Sub Region – all sub-regions for APAC and AMER |  | Stage | Prod | Dev Team | High | To Do
244 |  | Lookup | Lookup: Teams – all team names and routing codes present |  | Stage | Prod | Dev Team | High | To Do
245 |  | Lookup | Lookup: Validation_Types – all validation type rules present | Regex and rule metadata used by validationSummary action | Stage | Prod | Dev Team | High | To Do
246 |  | Lookup | Lookup: Users – user list populated |  | Stage | Prod | Dev Team | Medium | To Do
247 |  | Lookup | Lookup: Business Unit – all business units present |  | Stage | Prod | Dev Team | High | To Do
SECTION 8 – VALIDATION RULES
248 |  | Rules | Email SFDC Campaign ID rule loaded | Regex: ^701[A-Za-z0-9]{15}$ ¦ Advice: Must start with 7011 or 701Ke | Stage | Prod | Dev Team | High | To Do
249 |  | Rules | Preview Text length rule loaded | Regex: ^.{40,130}$ ¦ 40–130 characters | Stage | Prod | Dev Team | High | To Do
250 |  | Rules | Subject line length rule loaded | Regex: ^.{0,89}$ ¦ Max 90 characters | Stage | Prod | Dev Team | High | To Do
251 |  | Rules | Email CTA Link format rule loaded | Regex: ^$¦^(https?:\/\/)[^\s]+$ ¦ Valid HTTPS URL | Stage | Prod | Dev Team | High | To Do
252 |  | Rules | SFDC Internal Campaign ID rule loaded | Regex: ^701[A-Za-z0-9]{15}$ ¦ 18 chars, starts 7011/701Ke | Stage | Prod | Dev Team | High | To Do
253 |  | Rules | Banner Image URL format rule loaded | Regex: ^$¦^(https?:\/\/)[^\s]+$ ¦ Valid HTTPS URL | Stage | Prod | Dev Team | High | To Do
254 |  | Rules | Marketing Hub URL format rule loaded | Regex: ^$¦^(https?:\/\/)[^\s]+$ ¦ Valid HTTPS URL | Stage | Prod | Dev Team | High | To Do
255 |  | Rules | CTA URL parameter validation active: s_iid, s_rtid mandatory; trackingid, mv, click advisory by region | Validated per region (AMERICAS vs APAC) inside validationSummary action | Stage | Prod | Dev Team | High | To Do
SECTION 9 – MARKETO TOKENS & MCZ
256 |  | Tokens | All 77 tokens verified in PROD Marketo Program Shell – APAC | Tokens created at 100% MCZ Pre-Build task completion | Stage MCZ | Prod MCZ | Ops Team | High | To Do
257 |  | Tokens | All 77 tokens verified in PROD Marketo Program Shell – AMER |  | Stage MCZ | Prod MCZ | Ops Team | High | To Do
258 |  | Tokens | Common tokens S.No 1–33 verified (coded_folder_name, Fiscal_FY, Fiscal_M, Fiscal_Q, Hardcoded POI, POI, Program Shell Abbreviation, Region, Sub Region, Request ID, Scheduled Date, Solutions, Solutions Abbreviations, From Name, From Address, Reply-To, Language, Email Subject, Preview Text, Headline, Banner Image, Email Body, CTA Text, CTA Link, SFDC IDs, click) | See token table in technical documentation | Stage | Prod | Ops Team | High | To Do
259 |  | Tokens | CTA section tokens 2–5 verified (Email Headline, Body, Image, CTA Text, CTA Link, SFDC Vehicle/Internal Campaign ID, SFDC Offer ID, click per section) | Tokens S.No 34–73; one set per additional CTA section | Stage | Prod | Ops Team | High | To Do
260 |  | Tokens | APAC-specific tokens auto-created on MCZ provisioning verified |  | Stage MCZ | Prod MCZ | Ops Team | High | To Do
261 |  | Tokens | AMER-specific tokens auto-created on MCZ provisioning verified |  | Stage MCZ | Prod MCZ | Ops Team | High | To Do
262 |  | MCZ | SnapLogic PROD API confirmed connected to Marketo PROD (not sandbox) | Critical: confirm with SnapLogic team before go-live | Stage API | Prod API | Ops Team | High | To Do
263 |  | MCZ | SnapLogic document retrieval confirmed from PROD Workfront document section | Document ID lookup must resolve to PROD WF docs | Stage | Prod | Ops Team | High | To Do
264 |  | MCZ | Marketo PROD folder structure (program folders, shells) pre-verified | Ensure destination folders exist before first provisioning | Stage MCZ | Prod MCZ | Ops Team | High | To Do
SECTION 10 – NOTIFICATION EMAILS
265 |  | Emails | New Request Submitted: marketer receives confirmation email with request + project details | Triggered after scenario 01 project creation | Stage | Prod | Dev Team | High | To Do
266 |  | Emails | Language Task Update: marketer notified after language-specific task created in project | Triggered by scenario 02 | Stage | Prod | Dev Team | High | To Do
267 |  | Emails | Validation Summary: marketer receives validation result notification; also posted in project activity | Triggered by scenario 05.1 | Stage | Prod | Dev Team | High | To Do
268 |  | Emails | Assignment to Email Governance Team: correct regional team (APAC or AMER) notified with required action | Triggered by scenario 06 | Stage | Prod | Dev Team | High | To Do
269 |  | Emails | Email Governance Task Completion: marketer notified of approval; content change no longer allowed after this point | Triggered by scenario 07 | Stage | Prod | Dev Team | High | To Do
270 |  | Emails | Pre-Build Confirmation: Email Governance Team receives build details and required approval actions | Triggered after Email Program Summary task completion (scenario 11) | Stage | Prod | Dev Team | High | To Do
271 |  | Emails | Final MCZ Build Notification: confirmation sent after successful MCZ build | Triggered by scenario 15 success route | Stage | Prod | Dev Team | High | To Do
272 |  | Emails | All email notification links (project URLs, task URLs) point to PROD Workfront | Base URL must use PROD WF domain | Preview Base URL | Prod Base URL | Dev Team | High | To Do
SECTION 11 – INTEGRATION & END-TO-END TESTING
▸ E2E-01: APAC Single CTA – Full Flow
273 |  | E2E-01 | Submit APAC Single CTA request → correct project template selected (Email Blast-APAC-INF) |  | – | Prod | QA Team | High | To Do
274 |  | E2E-01 | Language dropdown populates APAC languages only (scenario 00 external lookup) |  | – | Prod | QA Team | High | To Do
275 |  | E2E-01 | APAC-specific targeting criteria fields mapped to task form (verticals, roles, personas, GTM segment, POI) |  | – | Prod | QA Team | High | To Do
276 |  | E2E-01 | Unused language tasks set to Cancelled; selected language task active |  | – | Prod | QA Team | High | To Do
277 |  | E2E-01 | Overview generated and posted on Issue, Project, and Language task |  | – | Prod | QA Team | High | To Do
278 |  | E2E-01 | Validation summary posted on task (no critical errors in clean test) |  | – | Prod | QA Team | High | To Do
279 |  | E2E-01 | Email Governance Team APAC assigned and notified |  | – | Prod | QA Team | High | To Do
280 |  | E2E-01 | Governance approves → project moved to Ops Queue, marketer notified, access revoked to VIEW |  | – | Prod | QA Team | High | To Do
281 |  | E2E-01 | Email Program Summary task completes → MCZ Pre-Build data (Shell, Name, Folder) populated in task form |  | – | Prod | QA Team | High | To Do
282 |  | E2E-01 | MCZ Build JSON assembled, uploaded as document to MCZ Pre-Build task section, notification posted |  | – | Prod | QA Team | High | To Do
283 |  | E2E-01 | SnapLogic PROD API called with correct document ID |  | – | Prod | QA Team | High | To Do
284 |  | E2E-01 | Marketo PROD: program shell created with all 77 tokens correctly populated |  | – | Prod | QA Team | High | To Do
285 |  | E2E-01 | SnapLogic success response → Marketo Program URL posted on project, Planning Sync Status updated to success |  | – | Prod | QA Team | High | To Do
▸ E2E-02: APAC Multi-CTA (3 CTAs)
286 |  | E2E-02 | Submit APAC Multi-CTA request selecting 3 CTAs → all 3 CTA content sections mapped to task form |  | – | Prod | QA Team | High | To Do
287 |  | E2E-02 | Validation: CTA URL parameters (s_iid, s_rtid) validated for all 3 CTA URLs |  | – | Prod | QA Team | High | To Do
288 |  | E2E-02 | Marketo: token sections 2 and 3 (CTA -2, CTA -3) generated in PROD program shell |  | – | Prod | QA Team | High | To Do
289 |  | E2E-02 | Full flow to MCZ success verified end-to-end |  | – | Prod | QA Team | High | To Do
▸ E2E-03: AMER Single CTA – Full Flow
290 |  | E2E-03 | Submit AMER Single CTA request → correct project template selected (Email Blast-AMER-INF) |  | – | Prod | QA Team | High | To Do
291 |  | E2E-03 | Enterprise GTM Segments field visible and mapped correctly (AMER only) |  | – | Prod | QA Team | High | To Do
292 |  | E2E-03 | AMER-specific targeting fields mapped (NOAM/LATAM segments, Product Buying Group, industry, suppressions, GM-SOR) |  | – | Prod | QA Team | High | To Do
293 |  | E2E-03 | AMER language dropdown populates AMER-specific languages only |  | – | Prod | QA Team | High | To Do
294 |  | E2E-03 | Full flow to MCZ success verified end-to-end |  | – | Prod | QA Team | High | To Do
▸ E2E-04: AMER Multi-CTA
295 |  | E2E-04 | Submit AMER Multi-CTA → multi-CTA token sections 2–5 generated correctly in Marketo PROD |  | – | Prod | QA Team | High | To Do
296 |  | E2E-04 | All AMER-specific fields validated (NOAM/LATAM Account Segment, Product Buying Group, Adobe Department, Job Level) |  | – | Prod | QA Team | High | To Do
▸ E2E-05: Email Governance Rejection
297 |  | E2E-05 | Governance rejects campaign → project status set to Cancelled |  | – | Prod | QA Team | High | To Do
298 |  | E2E-05 | Marketer receives rejection notification with reason |  | – | Prod | QA Team | High | To Do
299 |  | E2E-05 | No MCZ provisioning triggered after rejection |  | – | Prod | QA Team | High | To Do
▸ E2E-06: Validation Critical Failure
300 |  | E2E-06 | Submit with invalid SFDC ID → task flagged at 50% (blocked), marketer notified with correction link |  | – | Prod | QA Team | High | To Do
301 |  | E2E-06 | Submit with invalid CTA URL (no HTTPS) → critical flag raised, task blocked |  | – | Prod | QA Team | High | To Do
302 |  | E2E-06 | Non-critical issue (advisory) → soft note posted, task NOT blocked |  | – | Prod | QA Team | High | To Do
▸ E2E-07: SnapLogic Error Responses
303 |  | E2E-07 | Error 'parent folder not found' → error details posted on project, task reset to In Progress in Planning |  | – | Prod | QA Team | High | To Do
304 |  | E2E-07 | Error 'search key failure' → error handled, Planning Sync Status updated to error |  | – | Prod | QA Team | High | To Do
305 |  | E2E-07 | Error 'missing folder name or program name' → descriptive error with corrective action posted |  | – | Prod | QA Team | High | To Do
▸ E2E-08: APAC Campaign with Salesforce ID Generation = Yes
306 |  | E2E-08 | SFDC = Yes on APAC request → 2 APJ-specific Salesforce build tasks activated in APAC project (scenario 07 sub-route C) | Only applies to APAC; AMER bypasses this step | – | Prod | QA Team | High | To Do
307 |  | E2E-08 | Route 4 re-validation triggered before Ops pick-up (region = APAC + SFDC = Yes) |  | – | Prod | QA Team | High | To Do
SECTION 12 – POST-RELEASE SIGN-OFF
308 |  | Post-Release | First live APAC campaign request monitored end-to-end in PROD | Confirm all steps complete and Marketo program created | – | Prod | Ops Team | High | To Do
309 |  | Post-Release | First live AMER campaign request monitored end-to-end in PROD |  | – | Prod | Ops Team | High | To Do
310 |  | Post-Release | Hypercare period defined (recommended minimum 2 weeks) | On-call support defined for critical issues post go-live | – | Prod | Ops Team | High | To Do
311 |  | Post-Release | All PREVIEW Fusion scenarios in Stage deactivated or archived | Prevent accidental Stage runs interfering with PROD | Preview | – | Dev Team | Medium | To Do
312 |  | Post-Release | PROD Fusion scenario error notifications configured | Alert on scenario failure or error rate spike | – | Prod | Dev Team | High | To Do
313 |  | Post-Release | Workfront Planning data flow confirmed in PROD (records flowing correctly into all tables) | Spot-check 2–3 requests in Planning tables | – | Prod | Dev Team | High | To Do
314 |  | Post-Release | Operations team trained on PROD dashboards, workflows and escalation process |  | – | Prod | Ops Team | High | To Do
315 |  | Post-Release | Marketer team communication sent about new request process in PROD | Include how-to guide and support contact | – | Prod | Ops Team | Medium | To Do
316 |  | Post-Release | Stakeholder sign-off obtained from Marketing Operations lead | Written or email approval | – | Prod | Ops Team | High | To Do
317 |  | Post-Release | Go-live confirmation document completed (date, sign-off names, known issues) | Archive for audit trail | – | Prod | Ops Team | High | To Do
TOTAL CHECKLIST ITEMS: 317 ¦ Sections: Pre-Release (9) · Workfront Config (32) · Fusion Common (8) · Watch Events (24) · Webhook Scenarios (99) · Adobe I/O (17) · Planning Tables (25) · Validation Rules (8) · MCZ/Marketo (9) · Notifications (8) · E2E Testing (33) · Post-Release (10)